# Potential Merger — Discussion Transcript

Contoso Tobacco & Wellness · Confidential · Strategy & Corp Dev · 10 June 2026

# Meeting Details

Subject: Potential Merger — Project Horizon — Nusantara Wellness Foods

Date: 10 June 2026  ·  Duration: 58 minutes  ·  Channel: Microsoft Teams

Chair: Pak Hendra Susanto (General Manager · Indonesia)

Attendees: GM, CFO, COO, Head of Strategy, Head of HR, Head of Legal, External Advisor (boutique IB)

# Opening — context from the GM

Pak Hendra Susanto: "Thanks everyone. The Board has asked us to come back at the next session with a clear go / no-go view on Project Horizon. To recap — the target is Nusantara Wellness Foods, an Indonesian health-functional-foods manufacturer (~Rp 850 bn revenue) with BPOM-registered ginseng, royal-jelly and herbal-tonic SKUs and a strong modern-trade footprint. The strategic rationale is straightforward: it fast-tracks our entry into the Indonesian health-functional-foods category, leveraging KTNG&#39;s global ginseng heritage with a local BPOM-registered platform. Today I want us to pressure-test three things — the deal economics, the integration plan, and the deal-breakers. Let&#39;s keep this tight."

# Deal economics — CFO

CFO: "Headline number is USD 38m enterprise value (cash + 2-year earn-out). Our base case shows accretion from year two, assuming we capture about 60% of the identified synergies — principally cross-portfolio modern-trade leverage, shared trade-marketing, HQ G&amp;A consolidation, exporting Korean-ginseng IP into local SKUs. The downside case — synergies at 30%, integration costs 20% over — still clears our hurdle rate, but barely. Funding is a mix of operating cash and a new revolver; we have indicative term sheets from two banks."

Pak Hendra Susanto: "What kills the deal economics?"

CFO: "Three things — a 15%+ over-pay vs current ask, synergies coming in below 30%, or a material liability discovered in diligence. We have flagged all three in the risk register."

# Integration plan — COO

COO: "I would split the integration into three waves. Wave one is the back-office and supplier rationalisation in the first 90 days. Wave two is the operating-model harmonisation over months 4 to 9. Wave three — and this is the riskiest — is the front-line / customer-facing changes. My recommendation is to keep the front-line brand intact for the first 12 months. Day-one disruption is the biggest single risk to value."

COO: "I want to flag the concerns the team has surfaced: halal certification continuity (LPPOM-MUI); founder-CEO retention; BPOM permit transferability; brand-dilution risk if we co-mingle with the tobacco portfolio. None of these are deal-breakers on their own, but together they argue for a phased close and a strong retention package for the top 30 people on day one."

# People & culture — Head of HR

HR: "Two points. First, we will need a retention pool — my early estimate is 0.7% to 1.0% of deal value, ring-fenced for the top 30 to 50 employees. Second, the culture diagnostic should start before signing, not after. We have used a 10-day cultural-due-diligence approach before and it has paid for itself."

# Legal & regulatory — Head of Legal

Legal: "Filings will be required with KPPU (competition authority) and the sector regulator. We do not expect substantive issues, but the timeline is 90 to 120 days minimum. I would also recommend an MAC clause tightly drafted around the top three concerns the COO flagged."

# Decisions

Proceed with confirmatory due diligence; budget approved up to USD 350k for advisors.

CFO to refresh base / downside cases with sensitivity on the three deal-breakers identified.

COO to draft a 100-day integration plan covering Wave 1 only, for the next Board pre-read.

HR to scope the retention pool and a 10-day cultural-due-diligence approach.

Legal to circulate a draft MAC clause and a regulator timeline by end of next week.

Reconvene in two weeks; target Board decision at the next quarterly session.

# Action items

CFO — refreshed financial model with sensitivities — due in 10 working days.

COO — Wave-1 integration plan (back-office + supplier) — due in 10 working days.

HR — retention-pool sizing and cultural-DD scope — due in 7 working days.

Legal — draft MAC clause + regulator timeline — due in 5 working days.

Pak — Board pre-read consolidating the above — due 3 working days before next Board.

# Closing — GM

Pak Hendra Susanto: "Good discussion. Let me be clear on the bar: I want a clean recommendation — go or no-go — with the three deal-breakers tested and a retention plan that we can stand behind on day one. Thanks everyone."